# Terms of Reference

Working Group on Data for AI in Health (WG-Data)

Global Initiative on AI for Health (GI-AI4H)

ITU • WHO • WIPO

| Acronym | WG-Data |
| --- | --- |
| Full Name | Working Group on Data for AI in Health |
| Parent Body | Global Initiative on AI for Health (GI-AI4H) |
| Status | Active |

# 1. Background and Rationale

The rapid advancement of artificial intelligence in healthcare promises transformative improvements in diagnosis, treatment, and health system efficiency. However, the successful deployment of AI solutions in healthcare settings faces significant barriers related to data accessibility, quality, and interoperability.

Current healthcare systems encounter high transaction costs when implementing AI solutions due to:

- Complex and fragmented data preparation requirements across institutions

- Manual validation processes that do not scale

- Lack of standardized formats for healthcare AI datasets

- Privacy and regulatory constraints limiting data sharing

- Inadequate evaluation frameworks for Large Language Models (LLMs) in clinical contexts

- Limited mechanisms for secure, privacy-preserving data exchange

Building on the successful FG-AI4H assessment framework and recent advances in data specification standards (including the Croissant metadata format from MLCommons), WG-Data aims to significantly lower barriers to healthcare AI adoption while ensuring privacy, quality, and equitable access to data globally.

# 2. Scope

WG-Data addresses the critical challenge of data infrastructure for healthcare AI by developing standards, protocols, and best practices for secure and efficient data and model exchange. The working group operates at the intersection of machine learning, healthcare informatics, data governance, privacy engineering, and regulatory compliance.

## 2.1 In Scope

- Healthcare AI dataset indexing, cataloguing, and discoverability standards

- Data and Model Exchange Protocol (DMXP) specifications

- Healthcare-specific extensions to Croissant metadata format

- Privacy-preserving data sharing mechanisms (federated learning, differential privacy)

- Synthetic data generation standards and validation methods

- LLM evaluation frameworks and benchmarks for healthcare applications

- Quality management protocols for healthcare AI data assets

- Medical ontology compatibility (ICD, SNOMED CT, UMLS, HL7 FHIR)

## 2.2 Out of Scope

- Development of specific AI models or clinical decision support systems

- National or regional regulatory framework development

- Clinical validation of specific healthcare AI applications

# 3. Mandate and Objectives

WG-Data is mandated to develop normative guidance, technical specifications, and practical tools that enable the global health AI community to efficiently and safely exchange data and models.

## 3.1 Primary Objectives

- Establish data indexing good practices for healthcare AI datasets, incorporating harmonized data product standards supporting diverse healthcare data types.

- Build a catalogue meta-index across data vendors for unified browsing and loading of ML-ready healthcare datasets using standardized formats.

- Develop transaction protocols for secure ML asset exchange, including data authentication, usage rights management, and user authentication.

- Specify evaluation frameworks for assessing LLM performance in healthcare contexts, addressing clinical safety, hallucination detection, and domain-specific benchmarking.

- Conduct cross-sectorial federated testing of protocols in real-world healthcare environments across diverse user roles.

# 4. Work Streams

WG-Data organizes its activities into six interconnected work streams, each addressing critical aspects of healthcare AI data infrastructure.

## 4.1 Data Indexing and Cataloguing (WS-1)

Objective: Develop comprehensive standards for describing, indexing, and discovering healthcare AI datasets.

Key Activities:

- Define healthcare-specific extensions to Croissant metadata format

- Establish standardized formats for imaging (DICOM), genomics, EHR data (HL7 FHIR), and clinical notes

- Develop searchability mechanisms including graph-based and embedding-based approaches

- Ensure compatibility with medical ontologies (ICD-10/11, SNOMED CT, UMLS, LOINC)

- Create quality metadata standards including bias documentation and representativeness metrics

## 4.2 Transaction Protocols (WS-2)

Objective: Specify the Data and Model Exchange Protocol (DMXP) for secure healthcare AI asset transactions.

Key Activities:

- Data authentication mechanisms including digital signing and provenance tracking

- Usage rights specification and license management for data assets

- Data communication protocols compatible with Model Context Protocol (MCP)

- User authentication and authorization frameworks

- Audit trail specifications for regulatory compliance

## 4.3 Privacy-Preserving Data Exchange (WS-3)

Objective: Enable collaborative AI development while protecting patient privacy and meeting regulatory requirements.

Key Activities:

- Federated learning protocol specifications for multi-institutional healthcare AI training

- Differential privacy implementation guidelines for healthcare data

- Secure multi-party computation standards for sensitive medical data analysis

- Privacy attack mitigation strategies (model inversion, membership inference)

- Compliance mapping to GDPR, HIPAA, and emerging AI regulations

## 4.4 Synthetic Data for Healthcare AI (WS-4)

Objective: Establish standards for generating, validating, and using synthetic healthcare data for AI development.

Key Activities:

- Quality metrics for synthetic healthcare data (statistical fidelity, utility preservation)

- Privacy validation frameworks for synthetic data (re-identification risk assessment)

- Guidelines for synthetic data use in regulatory submissions and clinical validation

- Attribution and provenance standards for AI-generated synthetic datasets

- Bias assessment and mitigation in synthetic data generation

## 4.5 LLM Evaluation for Healthcare (WS-5)

Objective: Develop comprehensive evaluation frameworks and benchmarks for assessing Large Language Model performance in healthcare applications.

Rationale: While LLMs demonstrate promising capabilities on medical licensing exams, real-world clinical performance requires distinct evaluation approaches. Only 5% of published evaluations use real patient data, highlighting a critical gap between benchmark performance and clinical utility.

Key Activities:

### 4.5.1 Clinical Safety Evaluation

- Hallucination detection and quantification methods for medical contexts

- Medical misinformation identification and severity classification

- Harmful recommendation detection (contraindicated treatments, dangerous dosages)

- Red-teaming protocols for medical LLM safety assessment

### 4.5.2 Clinical Task Performance

- Diagnostic reasoning evaluation beyond multiple-choice accuracy

- Treatment recommendation assessment against clinical guidelines

- Clinical documentation quality metrics (summarization, note generation)

- Patient communication appropriateness evaluation

### 4.5.3 Benchmark Development

- Real-world clinical scenario datasets (beyond USMLE-style questions)

- Multi-lingual medical evaluation sets for global applicability

- Low-resource and rare disease evaluation benchmarks (tropical diseases, neglected conditions)

- Longitudinal evaluation protocols for model consistency over time

### 4.5.4 Fairness and Equity

- Demographic bias detection in LLM medical outputs

- Performance stratification by patient population characteristics

- Geographic and cultural appropriateness assessment

- Accessibility evaluation for diverse user populations

## 4.6 Implementation and Validation (WS-6)

Objective: Validate developed standards through real-world federated testing across diverse healthcare settings.

Key Activities:

- Cross-institutional pilot implementations in diverse geographic regions

- Multi-stakeholder testing across data vendors, healthcare providers, and AI developers

- Low and middle-income country (LMIC) implementation support and validation

- Interoperability testing with existing health information systems

- Reference implementation development and maintenance

# 5. Deliverables and Milestones

## 5.1 Short-Term (6-12 months)

- Healthcare Croissant Extension Specification v1.0

- Data indexing good practices document for healthcare AI datasets

- LLM healthcare evaluation framework requirements document

- Standardized formats specification for imaging, genomics, and EHR data

- Quality management protocols for data assets (initial version)

## 5.2 Medium-Term (12-24 months)

- Catalogue meta-index prototype enabling unified dataset browsing

- Data and Model Exchange Protocol (DMXP) v1.0 specification

- LLM Healthcare Evaluation Benchmark Suite (MedEval-GI)

- Synthetic data quality and validation guidelines

- Privacy-preserving federated learning reference architecture

- Ontology compatibility layer (ICD, SNOMED CT, UMLS mapping)

## 5.3 Long-Term (24-36 months)

- Cross-sectorial federated validation results report

- DMXP reference implementation and tooling

- Multi-lingual LLM evaluation benchmarks for 10+ languages

- LMIC-focused synthetic data generation toolkit

- ITU-T Recommendation candidate documents

# 6. Governance and Organization

## 6.1 Leadership

| Role | Name / Organization | Contact |
| --- | --- | --- |
| Co-Chair | Luis Oala, Dotphoton AG | luis.oala@dotphoton.com |
| Co-Chair | Marc Lecoultre, MLLab.ai | ml@mllab.ai |

## 6.2 Meeting Cadence

- Full working group: Monthly virtual meetings

- Work stream teams: Bi-weekly coordination calls

- In-person workshops: Aligned with GI-AI4H plenary meetings

## 6.3 Decision Making

Decisions are made by consensus of active members. In cases where consensus cannot be reached, matters are escalated to GI-AI4H leadership. Technical specifications require review by at least three independent experts before adoption.

# 7. Membership

## 7.1 Current Active Members

| Name | Institution | Country | Status |
| --- | --- | --- | --- |
| Ferath Kherif | CHUV | Switzerland | Active |
| Pradeep Balachandran | Engineering Consultancy | India | Active |
| Hend Abou El Nasr | Cairo University | UAE/Egypt | Active |
| Dominick Romano | Drainpipe.io | United States | Active |
| Dhanushi Hettiarachchi | Ophtha Innovations | Sri Lanka | Active |
| Nigel Foo | NUS | Singapore | Active |

## 7.2 Membership Criteria

Participation in WG-Data is open to all interested parties from ITU Member States, WHO Member States, academia, industry, civil society, and the technical community. Members are expected to:

- Actively contribute to at least one work stream

- Attend at least 50% of working group meetings

- Adhere to GI-AI4H code of conduct and intellectual property policies

- Declare any conflicts of interest

# 8. Relationships and Coordination

## 8.1 Internal Coordination (GI-AI4H)

- WG-Regulatory: Alignment on data governance and compliance requirements

- WG-Ethics: Ethical considerations in data collection and AI evaluation

- Topic Groups: Data requirements for specific medical AI applications

- Open Code Initiative: Platform integration and tooling alignment

## 8.2 External Liaison

- MLCommons Croissant Working Group: Healthcare extensions and medical data standards

- HL7 International: FHIR integration and clinical data interoperability

- SNOMED International: Terminology services and ontology alignment

- IEEE SA: AI standards harmonization

- ISO/IEC JTC 1 SC 42: AI standards coordination

- Hugging Face: Open Medical-LLM Leaderboard collaboration

# 9. Resources and Support

## 9.1 Secretariat Support

WG-Data receives administrative support from the ITU Telecommunication Standardization Bureau (TSB) and coordination support from WHO Digital Health and Innovation Department.

## 9.2 Funding

Working group activities are supported through GI-AI4H core funding. Travel support for LMIC participants may be available through Fondation Botnar grants. Members contribute in-kind through expert time and hosting of pilot implementations.

## 9.3 Tools and Platforms

- Collaboration: GI-AI4H collaboration portal and mailing lists

- Document Management: ITU-T collaboration platform

- Code Repository: GitHub (github.com/fg-ai4h)

# 10. Review and Amendments

This Terms of Reference shall be reviewed annually by WG-Data leadership in consultation with GI-AI4H governance. Amendments require approval by consensus of active members and notification to GI-AI4H secretariat.

# Approval

This Terms of Reference was approved by the Working Group on Data for AI in Health.

| Date | Co-Chair 1 | Co-Chair 2 |
| --- | --- | --- |
| [Date] | Luis Oala | Marc Lecoultre |